## Instructions
CLASSERA TASK TRACKER — UPLOAD TEMPLATE
HOW TO USE
1. Go to the 'Tasks' tab | Click the Tasks sheet at the bottom of this file
2. Fill in your tasks row by row | One task per row, starting from row 2
3. Use the dropdowns | Click any cell in Owner, Category, Priority, Status, Performance — a dropdown appears
4. Required fields marked with * | Task Name, Owner, and Status must be filled for every row
5. Save as .xlsx | File → Save As → Excel Workbook (.xlsx)
6. Upload to the dashboard | Open the HTML tracker → click ⬆ Upload Excel in the top bar
COLUMN GUIDE
A Task Name * | Required. Full description of the task.
B Owner * | Required. Select from dropdown. Creates owner automatically in the dashboard.
C Category | Optional. Choose from the 8 standard categories in the dropdown.
D Priority | Optional. Critical / High / Medium / Low. Defaults to Medium if blank.
E Due Date | Optional. Must be in YYYY-MM-DD format — e.g. 2026-03-31
F Status * | Required. Not Started / In Progress / Completed
G Performance | Optional. On Track / At Risk / Off Track
H Notes | Optional. Any additional context or remarks
IMPORTANT NOTES
⚠ Do NOT add, remove, or reorder columns — the uploader expects this exact column order.
⚠ Do NOT rename the 'Tasks' sheet.
⚠ Uploading replaces ALL existing data in the dashboard — make sure the file is complete.
⚠ Owner names are read from column B — they don't need to match a pre-set list.
⚠ Performance column uses: On Track / At Risk / Off Track (the emojis are display-only in the dashboard).

## _Ref (hidden)
Owners | Categories | Statuses | Priorities | Performance
Jearmine | CEO Decision | Not Started | Critical | On Track
Ola | Client Experience | In Progress | High | At Risk
Madani | Corporate Structure & Compliance | Completed | Medium | Off Track
Elias | Financial Health |  | Low
Hani | Growth & Revenue
Mahmoud | People & Organization
Mona | Product & Innovation
Ashraf | Standardize & Automate
Ibad
Farhan
Refai
Moataz
Anas
Tariq
Ehab

## Tasks
Task Name * | Owner * | Category | Priority | Due Date (YYYY-MM-DD) | Status * | Performance | Notes
Medical Insurance Contract for Oman | Jearmine | People & Organization | Critical | 2026-02-28 | In Progress | At Risk
Quarter gift for nominated employees | Jearmine | People & Organization | Low | 2026-03-30 | In Progress | On Track
Outsoursing companies (Qatar- kuwait) | Jearmine | People & Organization | Critical | 2026-03-30 | Not Started | On Track
Out soursing companies Oman | Jearmine | People & Organization | Critical | 2026-02-28 | In Progress | At Risk
Saudization Problem | Jearmine | Corporate Structure & Compliance | Critical | 2026-03-30 | In Progress | Off Track
Finalize Unbudgeted Hiring Approval | Ola | People & Organization | High | 2026-03-30 | In Progress | At Risk
Expedite hiring - Update dash board daily | Ola | People & Organization | Critical | 2026-03-30 | In Progress | On Track
Implement Hero of the Month program by product vertical | Jearmine | People & Organization | Medium | 2026-03-30 | Completed | On Track
Finalize all pending employee rights (commissions, travel dues, reimbursements, etc.) | Jearmine | People & Organization | Critical | 2026-03-30 | In Progress | At Risk
Full implementation to Zen HR | Jearmine | Standardize & Automate | Critical | 2026-03-30 | In Progress | On Track
Launch the new performance & reward framework (BVS/RBS or equivalent) | Ola | People & Organization | Critical | 2026-03-30 | Completed | On Track
Finalize and publish updated org structure, role clarity, and reporting lines for all departments | Ola | People & Organization | High | 2026-03-30 | In Progress | At Risk
Establish Talent pipeline | Ola | People & Organization | Critical | 2026-03-30 | In Progress | On Track
Close 100% of approved critical hires (budgeted / hire-to-project) within agreed timelines | Ola | People & Organization | Critical | 2026-03-30 | In Progress | At Risk
Launch a coin-based reward and recognition program. | Jearmine | People & Organization | Medium | 2026-03-30 | Not Started | At Risk
Send a weekly company calendar email | Ola | People & Organization | High | 2026-03-30 | In Progress | At Risk
Ramadan - Iftar across Classera | Jearmine | People & Organization | High | 2026-03-30 | Completed | Off Track
Enroll in Gov. Support Programs | Ola | People & Organization | Critical | 2026-03-30 | In Progress | At Risk
Approval Card : Over budget 17.65%- Motion graphics position | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | At Risk
Launch city-based sales playbooks for priority markets | Elias | Standardize & Automate | High | 2026-03-30 | In Progress | At Risk
Implement Sales Academy with demo scripts per product | Elias | Standardize & Automate | High | 2026-03-30 | In Progress | On Track
Launch Sales Referral Program | Elias | Growth & Revenue | Medium | 2026-03-30 | In Progress | At Risk
Structure sales team by Large / Medium / Small deals | Elias | Growth & Revenue | High | 2026-03-30 | Completed | On Track
Revamp and approve Sales Contract Templates | Elias | Growth & Revenue | High | 2026-03-30 | Not Started | At Risk
Finalize and enforce Pricing List & Pricing Policy | Elias | Growth & Revenue | Critical | 2026-03-30 | Not Started | Off Track
Separate sales teams into Dedicated LMS and Dedicated TMS teams | Elias | Growth & Revenue | High | 2026-03-30 | Completed | On Track
Appoint Saudi Country Manager | Madani | People & Organization | High | 2026-03-30 | In Progress | On Track
Form Saudi Government Sales Team (5 members) | Elias | People & Organization | High | 2026-03-30 | Not Started | At Risk
Sign contract with Dr. Nasir | Madani | People & Organization | High | 2026-03-30 | In Progress | On Track
Appoint Oman Country Manager (Dr Saif ) | Madani | People & Organization | Critical | 2026-03-30 | In Progress | On Track
Establish Omani sales team | Elias | People & Organization | High | 2026-03-30 | Not Started | At Risk
dentify and onboard priority Individual advisors and strategic contributors | Elias | Growth & Revenue | High | 2026-03-30 | Not Started | At Risk
Formalize engagement models (roles, scope, incentives) | Elias | Growth & Revenue | High | 2026-03-30 | Not Started | At Risk
Approve and roll out Revised Sales Incentive Plan | Elias | People & Organization | Critical | 2026-03-30 | In Progress | On Track
Integrate CRM across Thrust Booster | Elias | Standardize & Automate | High | 2026-03-30 | Completed | On Track
Establish Online Sales Team (SDR) | Elias | People & Organization | High | 2026-03-30 | Completed | On Track
Launch automated online sales flow | Elias | Standardize & Automate | High | 2026-06-30 | In Progress | On Track
Achieve human-less / minimal-touch sales model | Elias | Standardize & Automate | High | 2026-06-30 | Not Started | On Track
Activate Reseller Program | Elias | Growth & Revenue | High | 2026-03-30 | Not Started | At Risk
Activate Local Reseller Program | Elias | Growth & Revenue | High | 2026-03-30 | Not Started | At Risk
Complete Atlas acquisition business deal | Elias | Growth & Revenue | Critical | 2026-03-30 | Completed | On Track
Accelerate SIS sales pipeline and closures | Elias | Growth & Revenue | Critical | 2026-04-30 | Not Started | On Track
Standardize sales hiring & onboarding | Elias | Standardize & Automate | Medium | 2026-03-30 | Completed | On Track
Implement sales training and standard presentations | Elias | Standardize & Automate | Medium | 2026-03-30 | Completed | On Track
Apply rule to non-performing sales staff (2 consecutive quarters) | Elias | People & Organization | High | 2026-03-30 | Not Started | At Risk
Leverage the investors network for business development - Strategic Sales Initiative | Elias | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
Implement a Referral program with Edu stakeholders in a country - - Strategic Sales Initiative | Elias | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
Private Schools Playbook - Strategic Sales Initiative | Elias | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
Saudi Learning Passport - Strategic Sales Initiative | Elias | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
OmanTel Partnership Operating Model - Strategic Sales Initiative | Elias | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
JV MOE KSA with full financial modeling- Strategic Sales Initiative | Elias | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
Implement a commission structure based on product revenue | Elias | People & Organization | Critical | 2026-03-30 | In Progress | At Risk
Elias: wants meeting with Madani, Mostafa and Moataz ASAP to close on the private schools offers for Oman | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Elias: need your help to close whatever is pending with Abdallah Al bahraini | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Mostafa: said "The CEO asked me to send the offer to share it with Shawamer" - Remind | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Elias: need CEO to introduce him to the Pure consulting firm | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Elias: can Madani pls connect me with our Qatari investor to sync with him on the Qatar opportunity? | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Elias: also need access to the minister of Edu in Qatar asap pls to push our agenda at the highest level | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Elias: also need Madani pls to connect with the Egyptian minister and get us an update on where we are and next steps | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Elias: What are the next steps about Syria, as per Madani, as he might have had side talks during BETT | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Malisho: Syria – Ministry of Communications Agreement (requested by the ministry to proceed) | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Malisho: Syria – Ministry of Health (Proposed Agreement) to enable us to formulate and submit the financial proposal | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Elias: A draft plan to train 1 million citizens annually on AI (as agreed with MCIT) is ready and awaiting your review and approval before being presented to MCIT. | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Elias : Made job description for the country manager role. he put one for Oman, that we can replicate for Saudi and Pakistan. | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Elias : interviewed the candidate for Pakistan and sent my feedback to Ali Raja. Positive in general. It is definitely better if we meet more candidates | Madani | CEO Decision | Critical | 2026-03-30 | In Progress | On Track
Elias : need to agree with you on Dr Nasir expected scope, and if we sign the same agreement with him | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Elias : need to hire a senior manager for digital revenue - The job description is attached | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Mostafa : the updated Syria MOE agreement. I highlighted the changed in yellow. Please review and approve or send any comments. | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Mostafa : please add to the list Kuwait MOE, the CEO met Dr. Hamad Alhamad (minister assistant for education) in Oman. | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Approval Card : Elias : 7k$ additional travel budget for sales | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Approval Card : Mostafa : Syria MOE - MOU final draft for the CEO approval | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Approval Card : TMS opportunities in Pakistan. Price approval | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Approval Card : Referral Program Compensation | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Approval Card : Smart Island University contract terms approval | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Identify and classify schools by tier to guide service level, support intensity, and account ownership: VIP, VVIP | Hani | Client Experience | High | 2026-03-30 | In Progress | At Risk
Schedule school visits every semester calender | Hani | Client Experience | High | 2026-03-30 | In Progress | On Track
Implement P&L Account Ownership at Customer Level (Revenue, Cost-to-Serve, Margin) | Hani | Financial Health | Critical | 2026-03-30 | Not Started | At Risk
Launch Support 2.0 (Enhanced Support Model) | Hani | Standardize & Automate | Medium | 2026-03-30 | Not Started | At Risk
Tiered SLAs aligned with school tier (VIP / VVIP) | Hani | Standardize & Automate | Medium | 2026-03-30 | Not Started | On Track
Establish a dedicated Customer Experience Unit Focus areas: Customer surveys, Experience measurement, Voice of Customer (VoC), Ensure insights are fed into Product, Support, and Leadership | Hani | People & Organization | High | 2026-03-30 | In Progress | On Track
Candidate: Abwab (Jordanian-American) | Hani | People & Organization | High | 2026-03-30 | Not Started | On Track
Establish procedure for Formal customer sign-off on product roadmap | Hani | Standardize & Automate | High | 2026-03-30 | In Progress | On Track
Establish a centralized PMO Unit Reporting to: Hani & Chief of Staff | Hani | People & Organization | Critical | 2026-03-30 | In Progress | On Track
Launch Elite Program and it should be position as a profit center | Hani | Growth & Revenue | Low | 2026-06-30 | Not Started | On Track
Launch Certify Schools and Teachers 2.0, it should be position as a profit center | Hani | Growth & Revenue | Low | 2026-06-30 | Not Started | On Track
Launch Enrichment Initiatives (المبادرات الإثرائية), it should be position as a profit center | Hani | Growth & Revenue | Low | 2026-06-30 | Not Started | On Track
Establish a clear automation roadmap for all Activation Teams. Focus on:Eliminating manual effort, Improving scalability and speed | Hani | Standardize & Automate | High | 2026-05-30 | In Progress | At Risk
Establish structured focus groups | Hani | Client Experience | Medium | 2026-03-30 | In Progress | On Track
Establish Caden for Continuous communication and visits with middle schools (2nd and 3rd grade) | Hani | Client Experience | Medium | 2026-04-30 | In Progress | On Track
Establish procedure , Select and manage design partners | Hani | Product & Innovation | High | 2026-03-30 | Completed | On Track
Establish owner dashboards and reports | Hani | Standardize & Automate | Critical | 2026-06-30 | Not Started | At Risk
Define commission schema for: Strategic projects, VVIP accounts | Hani | People & Organization | High | 2026-03-30 | In Progress | On Track
Hani to nominate staff to work with Mona on monthly success stories | Hani | Growth & Revenue | High | 2026-03-30 | In Progress | On Track
Hani to decide on final date in December for Classera 16 | Hani | Product & Innovation | High | 2026-03-30 | Completed | On Track
Hani:Riyadh Schools have confirmed a meeting on Tuesday, 24 February from 12:00–1:00 PM and are requesting approval; if approved, we will also try to arrange a meeting with Al-Mutaqadimah on the same day | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Hani: coordinate Eng. Al-Madani’s first visit to Madinah to accompany him in visiting the major schools in the city: Elite (Al-Rayan, Al-Khandaq, and Al-Aqiq), due to its importance | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Hani: finalize the agreement with Atlas Company (Turkey) | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Hani: finalize the agreement with eMushrif | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Hani: finalize the agreement with GamaLearn | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Hani: Interview with the new Project Manager candidate – Oman | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Hani: Urgently contact Amer today and process his January salary today until a final agreement is reached with him. | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Hani: Urgently contact Mr. Mohammed Al-Khudair (National Company) due to the critical situation with the schools and the continuation of the current contract | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Hani: التواصل مع شركة عطاء لتجديد العقد لمدة ثلاث (3) سنوات، وقد تم إرسال نسخة الملحق عبر تطبيق واتساب إلى م. المدني | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Hani: توضيح الموقف بخصوص سحور وإفطار رمضان هل سيكون مخصصًا للموظفين والعملاء أم للموظفين فقط، مع التأكيد على المواعيد نظرًا لأهميتها | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Hani: اعتماد فئات مدارس النخبة (Elite Schools) حيث تم تصنيفها إلى الفئات التالية: Elite Partner - Special Partner - Value Partner | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Hani: تخصيص وقت لعرض مخرجاتنا في كل من VOC و Customer Journey | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Hani : نحتاج لترتيب اجتماع مع امين عام جمعيه خيركم | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Approval Card : Approval of a bonus payment for Eng. Omar Abu Salim for the delivery of the Judicial Center project (5 RVS). | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Approval Card : Halal Project Manager | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Approval Card : Approval for the payment of Amer’s End of Service entitlements (attached) | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Establish co-signature with growth department for each partnership type / track for each owner for the type/track | Mahmoud | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
Define a dedicated strategy for each partner, reviewed and planned on a quarterly basis. | Mahmoud | Growth & Revenue | Critical | 2026-03-30 | Not Started | At Risk
Set top-line revenue objectives for each partnership type, with specific focus on Top 10 strategic partners. | Mahmoud | Growth & Revenue | Critical | 2026-03-30 | Not Started | At Risk
Assign a Funding Manager or Funding Consultant responsible for Identifying relevant funding opportunities | Mahmoud | People & Organization | High | 2026-03-30 | Not Started | At Risk
Standardize the end-to-end partnership lifecycle, including:Partner selection criteria, Partner onboarding, Joint go-to-market execution | Mahmoud | Standardize & Automate | Critical | 2026-03-30 | Not Started | At Risk
KFUPM Partnership - Strategic Sales Initiative | Mahmoud | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
iCesco Partnership - Strategic Sales Initiative | Mahmoud | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
Mentor Partnership - Strategic Sales Initiative (TMS Freemium - Strategic Sales Initiative) | Mahmoud | Growth & Revenue | Critical | 2026-03-30 | Not Started | At Risk
ZenHR Partnership- Close on the partnership with ZenHR- Strategic Sales Initiative | Mahmoud | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
Funding for MOE Pakistan -Deliver the Pakistan study to the ICT minister - Strategic Sales Initiative | Mahmoud | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
Strategic Partners- Develop an annual plan with MSFT & AWS - Strategic Sales Initiative | Mahmoud | Growth & Revenue | Critical | 2026-03-30 | Not Started | At Risk
Partners GTM- Implement a partnership model with content providers, Edtech Partners and the eLearning center - Strategic Sales Initiative | Mahmoud | Growth & Revenue | Critical | 2026-03-30 | Not Started | At Risk
Hire sponsorship agency from Egypt for Innoxera Oman | Mahmoud | Growth & Revenue | High | 2026-03-30 | Completed | Off Track
Hire sponsorship agency from KSA for Innoxera KSA | Mahmoud | Growth & Revenue | High | 2026-03-30 | Completed | Off Track
Ensure Partnership Qualified Pipeline is entered in HubSpot and presented as part of the Star Wars meeting | Mahmoud | Standardize & Automate | High | 2026-03-30 | Completed | On Track
Finalize EdTech Focus Strategy with three partners (Bundle Scaling Partners) | Mahmoud | Growth & Revenue | Critical | 2026-03-30 | Not Started | At Risk
Integrate iFrame feature with Sandbox, enabling partners to open their page directly within Sandbox | Mahmoud | Product & Innovation | High | 2026-03-30 | Not Started | At Risk
For EdTech Sales OKRs, split targets into Training Content vs. EdTech | Mahmoud | Growth & Revenue | High | 2026-03-30 | Completed | On Track
Hire the Donors Organization Manager | Mahmoud | People & Organization | High | 2026-03-30 | Not Started | At Risk
Gabry : Sign the consultant agreement with the Funding Consultant nominated by Madani | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Gabry : Hiring Funding Consultant – 2 months | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Gabry : Reminder about the consultant agreement provided by legal department | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Gabry : Country Manager benefits | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Gabry : The notification period for resigned employees in Egypt is (45 days or 2 months) | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Gabry : Setting Zen <> HR meeting sponsored by CEO | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Gabry : Meeting with Pakistan Consultant company (Impetus) for Pakistan Study | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Gabry : Mahmoud Shares certificate value had not been communicated | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Gabry : Approval on the protocol of collaboration with ICESCO | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Gabry : EdgeX agreement with MoE Saudi seems very tricky | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Gabry : The exact venue and confirmed date for InnoXera Saudi/EdgeX | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Gabry : L&D consultant and Edtech sales in KSA (Hiring) | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Gabry : We only have now Egyptian Japanese Schools for the pilot. I tried to reach Dr. Ayman few times to provide introduction to government schools without success. We need your urgent support to communicate with the Minister to deliver on what he promised us | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Approval Card : CEO ICESCO Initiative business terms to be shared with ICESCO | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Approval Card : Selah El Telmeez Business Model for Egypt MoE Project | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Approval Card : 500 USD to support Partnerships Director visit to Riyadh in Iftar (meeting stakeholders) | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Create marketing materials for each product, including:Videos, Brochures, Company profile | Mona | Growth & Revenue | High | 2026-04-30 | Not Started | On Track
finalize InnoXera Deal with Saudi Ministry | Mona | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
Establish InnoXera Deal – Oman (EdTech Profit Center) | Mona | Growth & Revenue | Critical | 2026-03-30 | Not Started | At Risk
Hire InnoXera Manager | Mona | People & Organization | Medium | 2026-03-30 | Not Started | At Risk
Register InnoXera as a Trademark in SA | Mona | Corporate Structure & Compliance | High | 2026-03-30 | Completed | On Track
Launch C-Pay Video (Urgent) | Mona | Growth & Revenue | High | 2026-03-30 | Not Started | At Risk
Prepare and finalize C-Pay Marketing Materials and Bundles | Mona | Growth & Revenue | High | 2026-03-30 | Not Started | At Risk
Complete and open the Oman Office (Ashraf Fadeel ) | Ashraf | People & Organization | Critical | 2026-03-30 | Completed | On Track
Complete and open the Egypt Office (Ashraf Fadeel ) | Ashraf | People & Organization | Critical | 2026-03-30 | Completed | On Track
Csmarx location transfer to new area (Ashraf Fadeel) | Ashraf | People & Organization | High | 2026-03-30 | In Progress | On Track
Marketing Campaign for Oman Deployment | Mona | Growth & Revenue | High | 2026-03-30 | Not Started | At Risk
Aprroval Card : New Hiring Salary – 18% Increase Approval Request– Video Animator: 1,500 USD Net (without MVS) Content & Tools Specialist: 400 USD Net (without MVS) | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Approval Card : Additional cost of USD 1,800 for 40 extra attendees at the Egypt Iftar. | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Establish Partnership with established PTSP - HyperPay and checkout.com | Ibad | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
Plan for the $1B Challenge: Key challenges, Incentive framework, Team awareness and alignment | Ibad | Growth & Revenue | Critical | 2026-03-30 | In Progress | At Risk
Establish Agreement with a Financing Partner | Ibad | Growth & Revenue | High | 2026-03-30 | In Progress | On Track
Establish Agreement with an Open Banking | Ibad | Growth & Revenue | High | 2026-05-30 | In Progress | Off Track
Establish Agreements with the Top Five Fintech Companies | Ibad | Growth & Revenue | High | 2026-05-30 | In Progress | At Risk
Achieve 80% School Adoption of C-Pay (Reverse Plan) | Ibad | Growth & Revenue | Critical | 2026-09-30 | In Progress | Off Track
Partnership with the Private Education Committee | Ibad | Growth & Revenue | Medium | 2026-09-30 | Not Started | On Track
Partnership with the Madrasati Platform and the Ministry of Education | Ibad | Growth & Revenue | Medium | 2026-09-30 | Not Started | On Track
Plan for the Oman Ministry of Education Deal | Ibad | Growth & Revenue | High | 2026-09-30 | In Progress | At Risk
Establish a strategic agreement targeting 80% adoption of C-Pay and government certificate services | Ibad | Growth & Revenue | High | 2026-09-30 | In Progress | At Risk
Establish a parallel agreement to achieve 80% adoption within the private education sector | Ibad | Growth & Revenue | High | 2026-09-30 | In Progress | At Risk
Replicate the Model in Egypt | Ibad | Growth & Revenue | Medium | 2026-06-30 | Not Started | On Track
Replicate the Model in Syria | Ibad | Growth & Revenue | Medium | 2026-09-30 | Not Started | On Track
Replicate the Model in Bahrain | Ibad | Growth & Revenue | Medium | 2026-06-30 | Not Started | On Track
Unified Fintech Platform for the Education Sector | Ibad | Product & Innovation | High | 2026-05-30 | In Progress | At Risk
Financing solutions | Ibad | Product & Innovation | High | 2026-03-30 | Completed | On Track
Payment gateway | Ibad | Product & Innovation | High | 2026-03-30 | Completed | On Track
Fintech partner ecosystem | Ibad | Product & Innovation | High | 2026-03-30 | In Progress | At Risk
Float and settlement management | Ibad | Product & Innovation | High | 2026-03-30 | Completed | On Track
Register C-Pay in Egypt | Ibad | Corporate Structure & Compliance | Low | 2026-04-30 | In Progress | On Track
Establish C-Pay as a Standalone Company (Curve Out) | Ibad | Corporate Structure & Compliance | Low | 2026-04-30 | Not Started | On Track
Register C-Pay in Oman | Ibad | Corporate Structure & Compliance | Low | 2026-05-30 | Not Started | On Track
Enhance UI / UX for C-Pay | Ibad | Product & Innovation | High | 2026-04-30 | In Progress | Off Track
Benchmark against best-in-class platforms (e.g., “Dream”) | Ibad | Product & Innovation | High | 2026-04-30 | In Progress | At Risk
Position C-Pay as a fully standalone product | Ibad | Product & Innovation | High | 2026-03-30 | In Progress | At Risk
C-Pay Legal Entity & KSA License | Ibad | Corporate Structure & Compliance | High | 2026-04-30 | In Progress | On Track
Replace School Corner’s physical logistics with Z Company through a co-branded solution. | Ibad | Product & Innovation | Medium | 2026-06-30 | Not Started | On Track
Achieve 70% adoption of the co-branded solution by the next academic year. | Ibad | Product & Innovation | Medium | 2026-09-30 | Not Started | On Track
Complete the layoff of unnecessary roles and restructure the organization to be lean and efficient by next week. | Ibad | People & Organization | High | 2026-03-30 | In Progress | On Track
Build and scale a core EdTech platform in collaboration with five design partners. | Ibad | Product & Innovation | High | 2026-05-30 | In Progress | At Risk
Enable and onboard the top 10 EdTech companies onto the platform | Ibad | Growth & Revenue | High | 2026-03-30 | Not Started | On Track
فكه acquisition decision. | Ibad | Growth & Revenue | High | 2026-03-30 | Completed | On Track
“Bite” acquisition decision | Ibad | Growth & Revenue | High | 2026-03-30 | Completed | On Track
Ibad: School Matters (Al-Andalus - Al-Mishkaah - Al Tarbeya Al Islameya) | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Ibad: People Issues (Abdullah Babtain - Saleh Hafez - EduMalls Team members) | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Ibad : Need to discuss right way to promote B2C modules in the LMS or TMS | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Ibad : Marketing Video | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Approval Card : Urgent Retention Case for Abdullah Babtain | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Approval Card : 10% Increase Post Probation for Saleh Hafez | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Select two advisors for each product | Farhan | People & Organization | Medium | 2026-03-30 | Not Started | On Track
Finalize business case decision to Outsource:UI / UX | Farhan | Product & Innovation | Medium | 2026-03-30 | Not Started | On Track
Establish Mobile-First Strategy | Farhan | Product & Innovation | Critical | 2026-03-30 | In Progress | On Track
LMS Rewrite : Transition to a microservices architecture Phase 1 - Exam Service | Farhan | Product & Innovation | High | 2026-03-30 | In Progress | On Track
Recommended Decision Framework Build vs. Partner vs. Buy, including technical assessment for: | Farhan | Product & Innovation | High | 2026-03-30 | In Progress | On Track
المصروف المدرسي (School Fees / Allowance)--Short Term Fakkah, Long Term Static payment Link through Cpay | Farhan | Product & Innovation | High | 2026-03-30 | In Progress | On Track
Fakkah --المقصف (Cafeteria) | Farhan | Product & Innovation | High | 2026-03-30 | In Progress | On Track
--Fakkah عيادة مدرسية (School Clinic) | Farhan | Product & Innovation | High | 2026-03-30 | In Progress | On Track
Fakkah الباصات (Transportation / Buses) | Farhan | Product & Innovation | High | 2026-03-30 | In Progress | On Track
Integrate with data analytics tools across( MixPanel & Amplitude) the products " C-Smarx NOT included " phase 1 Small Grroup of School | Farhan | Standardize & Automate | High | 2026-03-30 | In Progress | On Track
Prooduct Calender With a clear approval cycle | Farhan | Product & Innovation | Critical | 2026-03-30 | In Progress | On Track
Establish Sign-off Process and procedure : VIP, VVIP | Farhan | Client Experience | High | 2026-03-30 | Completed | On Track
Create Focus Groups | Farhan | Client Experience | Medium | 2026-03-30 | In Progress | On Track
AI Benchmarking: List and benchmark AI capabilities on analysis and benchmarking websites | Farhan | Product & Innovation | High | 2026-03-30 | In Progress | On Track
Finalize Roadmap for Each Product for Q4 | Farhan | Product & Innovation | Critical | 2026-03-30 | In Progress | On Track
Finalize API Sandbox: Integration with full documentation, Definition of Done (DoD), Phase 1 and Phase 2 | Farhan | Product & Innovation | High | 2026-03-30 | In Progress | On Track
SIS :Prepare Technical Features and data sheet for Presales & Marketing . Conduct Training | Farhan | Product & Innovation | Medium | 2026-03-30 | Not Started | On Track
Update technology: Rewrite apps / database | Refai | Product & Innovation | Medium | 2026-03-30 | In Progress | On Track
Finalize Marketplace for MOEs | Farhan | Product & Innovation | Critical | 2026-03-30 | In Progress | On Track
MOE Qatar – AI Enhancement | Farhan | Product & Innovation | Critical | 2026-03-30 | Completed | On Track
Final Kuwait visits for AFAQ school and confirm two-year Csmarx Product Roadmap with AFAQ | Farhan | Product & Innovation | High | 2026-03-30 | Not Started | At Risk
Evaluate concept of using C-Smart outside KSA and C-SmarX within KSA | Farhan | Product & Innovation | High | 2026-03-30 | Not Started | At Risk
Product team to present Innovation Feature for Innoxera | Farhan | Product & Innovation | High | 2026-03-30 | In Progress | On Track
Include Sanabel Initiative as part of the Product Roadmap | Farhan | Product & Innovation | High | 2026-03-30 | In Progress | On Track
Finalize C-Pay WhatsApp (scope, roadmap, and release plan) - both reminder notifications as well as Pay By Link by mid of December, for 2nd semester readiness | Farhan | Product & Innovation | Critical | 2026-03-30 | Completed | On Track
Refai : The budget for the CSmarX Engineering Manager remains a primary bottleneck | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Refai : ATLAS is not deploy their SIS solution since the agreement is not signed | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Refai : ATLAS is not part of the current interviews cycle | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
New Cayman company establishment for Cxeed, JV for Cxeed Investment | Moataz | Corporate Structure & Compliance | High | 2026-03-30 | In Progress | On Track
New drafts for all contracts (Sales & Partnership) | Moataz | Corporate Structure & Compliance | High | 2026-03-30 | In Progress | At Risk
Due diligence (Contracts > $100,000 USD) | Moataz | Corporate Structure & Compliance | Medium | 2026-03-30 | In Progress | At Risk
GCC Corporate compliance checklist (Labor Law) | Moataz | Corporate Structure & Compliance | High | 2026-03-30 | In Progress | On Track
Contract Management System (Mission Control) | Moataz | Standardize & Automate | High | 2026-03-30 | Not Started | On Track
Implement Group-Wide Contract Delegation of Authority (DoA) | Moataz | Corporate Structure & Compliance | Medium | 2026-03-30 | In Progress | On Track
Cxseed agreement and contract for startup companies -Term Sheet | Moataz | Corporate Structure & Compliance | High | 2026-03-30 | In Progress | On Track
Establish legal entities for Kuwait | Moataz | Corporate Structure & Compliance | Medium | 2026-03-30 | In Progress | On Track
Establish legal entities for Bahrain | Moataz |  | Critical | 2026-03-30 | In Progress | On Track
C-pay Establishing Company decisions: list of decisions | Moataz | Corporate Structure & Compliance | High | 2026-03-30 | In Progress | On Track
Signing and sending UAE apps : Change owner from Madani to Classera | Moataz | Corporate Structure & Compliance | Critical | 2026-03-30 | In Progress | At Risk
implement Employee Stock Ownership Plan (ESOP) contracts. | Moataz | People & Organization | Critical | 2026-03-30 | In Progress | At Risk
Sanabil commercial terms approval (Atlas deal) | Moataz | Growth & Revenue | Critical | 2026-03-30 | Completed | On Track
Establish legal entities for Qatar | Moataz | Corporate Structure & Compliance | Medium | 2026-03-30 | In Progress | On Track
Classera Pakistan establishing company (awaiting lawyer) | Moataz | Corporate Structure & Compliance | Medium | 2026-04-30 | In Progress | On Track
Referral Agreement | Moataz | Growth & Revenue | High | 2026-04-30 | In Progress | On Track
Tax health check for Jordan and KSA entities. | Anas | Financial Health | High | 2026-04-30 | Completed | On Track
Approval of board resolutions for the June audited financials. | Anas | Financial Health | High | 2026-03-30 | Completed | On Track
Approval of board resolutions for establishing Qatar and Bahrain entities. | Moataz | Corporate Structure & Compliance | High | 2026-03-30 | Completed | On Track
Approval of board resolutions for the UAE entity share transfer. | Moataz | Corporate Structure & Compliance | High | 2026-03-30 | Completed | On Track
Etimad access: We urgently need a finance user to proceed with collections | Moataz | Corporate Structure & Compliance | High | 2026-03-30 | In Progress | Off Track
Updated certificate for Expert Solutions to enable change of bank authority | Anas | Corporate Structure & Compliance | Critical | 2026-03-30 | In Progress | Off Track
NDTP (National Digital Transformation Program) | Anas | People & Organization | Critical | 2026-04-30 | In Progress | At Risk
CEO on-time monthly management reporting (by 13th) | Anas | Financial Health | Critical | 2026-03-30 | In Progress | On Track
CEO Monthly budget variance reporting (Total & Departmental) | Anas | Financial Health | High | 2026-04-30 | In Progress | On Track
Monthly Recurring vs non-recurring cost | Anas | Financial Health | Medium | 2026-03-30 | In Progress | On Track
Monthly project budget tracking report issued | Anas | Financial Health | Critical | 2026-03-30 | Not Started | On Track
Pricing & packaging finalized (by product) startingg with Egypt | Anas | Growth & Revenue | Critical | 2026-05-30 | Not Started | At Risk
Monthly Headcount budget compliance Report | Anas | Financial Health | Critical | 2026-05-30 | Not Started | On Track
Discount approvals via authority matrix (Post Procing ) | Anas | Growth & Revenue | Critical | 2026-03-30 | Not Started | On Track
Maintain a Quarterly forcast business model showing 5-year impact on revenue, margin, and cash flow | Anas | Financial Health | High | 2026-03-30 | Completed | On Track
Implement cost & revenue center structure with time tracking for accurate cost allocation | Anas | Financial Health | Critical | 2026-03-30 | Completed | At Risk
Unify the financial year across all entities and update the Articles of Association (AoA) accordingly | Moataz | Corporate Structure & Compliance | Medium | 2026-03-30 | Not Started | On Track
Manage collection projects and legal recovery actions | Anas | Financial Health | Critical | 2026-03-30 | In Progress | On Track
Implement scenario modeling (base, upside, downside cases) | Anas | Financial Health | High | 2026-04-30 | Completed | On Track
CEO unit economics and profitability analysis by product and customer & Geography | Anas | Financial Health | Critical | 2026-03-30 | Completed | On Track
Manage tax compliance across KSA, Oman, Jordan, Egypt, and Delaware | Anas | Corporate Structure & Compliance | High | 2026-03-30 | In Progress | On Track
Ensure compliance with VAT, WHT ( For this year is clear ) | Anas | Corporate Structure & Compliance | High | 2026-03-30 | Completed | On Track
Implement transfer pricing compliance frameworks | Anas | Corporate Structure & Compliance | Medium | 2026-03-30 | Not Started | On Track
Execute tax optimization initiatives and manage external tax consultants | Anas | Financial Health | Critical | 2026-03-30 | In Progress | On Track
Lead ERP upgrade initiatives | Anas | Standardize & Automate | Critical | 2026-06-30 | In Progress | On Track
Implement BI dashboards and financial analytics tools (e.g., Power BI) | Anas | Standardize & Automate | Critical | 2026-03-30 | In Progress | On Track
Deliver structured reporting for small and strategic investors | Anas | Financial Health | Critical | 2026-06-30 | Completed | On Track
Complete remaining Series A requirements and related deliverables (KYC) | Anas | Financial Health | Critical | 2026-06-30 | In Progress | On Track
Develop standardized quarterly investor reporting packs (Big Investors ) | Anas | Financial Health | Critical | 2026-03-30 | Completed | On Track
Develop a funding strategy roadmap | Anas | Financial Health | Critical | 2026-04-30 | Not Started | On Track
Launch group-wide cost optimization initiatives | Tariq | Financial Health | Critical | 2026-03-30 | In Progress | At Risk
Finalize Legal SLA | Moataz | Standardize & Automate | High | 2026-06-30 | In Progress | On Track
Finalize advisor / Consultant agreement (commission and/or stock options) | Moataz | People & Organization | Critical | 2026-03-30 | In Progress | On Track
Finalize e-signature workflow for contracts | Moataz | Standardize & Automate | High | 2026-06-30 | In Progress | On Track
Prepare authorization of signature structure for sales staff- DOA | Moataz | Corporate Structure & Compliance | Low | 2026-03-30 | In Progress | On Track
Conduct a full review and update of all staff contract templates in Egypt, Jordan, KSA, and other regions | Moataz | Corporate Structure & Compliance | Critical | 2026-03-30 | In Progress | On Track
Finalize Oman Legal Entity Managing Director appointment | Moataz | People & Organization | Critical | 2026-03-30 | Not Started | On Track
Finalize SLA for Sales Contracts (from initiation to signing) | Moataz | Standardize & Automate | High | 2026-03-30 | In Progress | On Track
Finalize and sign agreement with Khalid Bahgat Office for collections | Anas | Financial Health | High | 2026-03-30 | Completed | On Track
Launch legal collection cases with two selected clients only | Moataz | Financial Health | Medium | 2026-03-30 | Not Started | On Track
Evaluate and validate compliance with Full-Time Remote Pass | Moataz | Corporate Structure & Compliance | Medium | 2026-03-30 | Not Started | On Track
Finalize Lease Agreements for Oman and Egypt Offices with the contractor | Moataz | People & Organization | Critical | 2026-03-30 | Completed | On Track
Review the Saudi Unicorns Program file - sent by email | Moataz | Corporate Structure & Compliance | Low | 2026-04-30 | Completed | On Track
Provide a list of any penalties the company has paid or that are still due since the beginning of July | Anas | Corporate Structure & Compliance | Medium | 2026-03-30 | Completed | On Track
Combined Board Resolutions and Share Issuance- Expert Solution | Moataz | Corporate Structure & Compliance | Critical | 2026-03-30 | In Progress | On Track
CRسداد فاتورة وزارة الاستثمار للحلول الخبيرة | Anas | Corporate Structure & Compliance | High | 2026-03-30 | Completed | On Track
Finance : asked for a Meeting to discuss forecast scenarios | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Finance : asked for a Meeting to review segment reporting and key findings | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Finance : asked for a Meeting to discuss collection status and old customer issues | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Finance : Oman – Bank authorities | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Finance : Delaware: Bank statements required since 2019 or the available data | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Finance : asked for a Meeting for Collections Commission Policy | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Finance : Collection of remaining Series A | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Approval Card : Offices Fund | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Approval Card : Collections Commission Policy | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Approval Card : Oman SIS project over budget staffing | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Moataz : Eng. Madani sign on docu sign Atlas Agreement | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Moataz : Cxseed: term sheet & Board approval on establishing the company in Cayman | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Moataz : Innoxera TM | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Moataz : Kuwait POA | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Moataz : C-pay decisions | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Moataz : UAE signing of apps | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Moataz : Esop Memo | Madani | CEO Decision | Critical | 2026-03-30 | In Progress | On Track
Moataz : Expert solutions | Madani | CEO Decision | Critical | 2026-03-30 | Completed | On Track
Moataz : Establishing of a new Classera Company in Cayman for the IP | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Moataz : Eng. Madani to share the contacts of the new Saudi firm | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Moataz : need quick discussion about King Fahd Agreement | Madani | CEO Decision | Critical | 2026-03-30 | Not Started | On Track
Implement Authority Matrix and & Bank Authority Matrix | Ehab | Corporate Structure & Compliance | High | 2026-03-30 | Not Started | On Track
Csmar: Build vs. Acquire (Pioneers vs. other segments) | Ehab | Product & Innovation | Critical | 2026-03-30 | Not Started | On Track
Finalize SLA for Finance, CFD, and Legal | Ehab | Standardize & Automate | High | 2026-03-30 | Not Started | On Track
Finalize and publish updated Classera Master Calendar | Ehab | People & Organization | High | 2026-03-30 | In Progress | On Track
Establish Vertical Squad Teams across all functions for each product (Product-Based Org Structure) and begin meetings: | Ehab | People & Organization | High | 2026-03-30 | In Progress | On Track
Ensure all CSAT are drafted by relevant departments, reviewed, and approved by the CEO Office; results to be generated and consolidated | Ehab | Standardize & Automate | High | 2026-03-30 | In Progress | On Track
Hire Naim El Din El Homsy as Advisor - Strategic Sales Initiative | Ehab | People & Organization | High | 2026-03-30 | Not Started | On Track
Conduct a comprehensive analysis and develop a strategic structured roadmap to achieve profitability. | Ehab | Financial Health | Critical | 2026-03-30 | Not Started | On Track
Deliver the revamp investment business case for LMS | Temraz | Product & Innovation | High | 2026-03-30 | Completed | On Track
Deliver the revamp investment business case for LMS 2 | Temraz | Product & Innovation | High | 2026-03-30 | Completed | On Track